## Core
TMP Cost Estimate
Project details
Client: |  | Hitachi
Project Description: |  | EVP Hypothesis
SOP Number: |  | 525634
Client contact: |  | Shannon Tracy
Date estimate produced: |  | 2025-09-10
Prepared by: |  | Ella Headlam
Version: |  | V.2
Brief / Scope
The RFP deliverables as defined by the brief. Phase 1: - Analysis of research - Internal - EVP framework development - standard costs
Price item description | Task detail | Job title | Hours | Rate £/hr | Third-party description | Line value | Item total | Item total
Part 1: Analysis of research - Internal | Review background docs and visionary materials - consolidate into high level actions for EVP | Employer Brand Strategist | 24 | 185 |  | 4440 | 59880 | 77844
| Map group company EVPs - provide full overview | Employer Brand Strategist | 20 | 185 |  | 3700
| Map group company EVPs - provide full overview | Employer Brand Researcher | 36 | 150 |  | 5400
| Map group company EVPs - produce high-level strawman of common links and themes | Employer Brand Strategist | 48 | 185 |  | 8880
| Map group company EVPs - Hypothesis EVP | Employer Brand Strategist | 12 | 185 |  | 2220
| Playback/Initial report | Employer Brand Strategist | 8 | 185 |  | 1480
| Playback/Initial report | Mac Operator High Spec | 16 | 110 |  | 1760
| Review of employee engagement survey - overlay against Hypothesis EVP | Employer Brand Strategist | 32 | 185 |  | 5920
| Review of employee engagement survey - overlay against Hypothesis EVP | Employer Brand Researcher | 24 | 150 |  | 3600
| Incorporate additional leader interview findings from Hitachi - revise the Hypothesis EVP | Employer Brand Strategist | 32 | 185 |  | 5920
| Incorporate additional leader interview findings from Hitachi - revise the Hypothesis EVP | Employer Brand Researcher | 24 | 150 |  | 3600
| Playback/Additional report stage | Employer Brand Strategist | 8 | 185 |  | 1480
| Playback/Additional report stage | Mac Operator High Spec | 16 | 110 |  | 1760
| Oversight | Employer Brand Insight and Planning Director | 4 | 260 |  | 1040
| Relationship Management | Client Manager | 16 | 130 |  | 2080
| Project Management | Project Manager | 60 | 110 |  | 6600
External qual research
Part 3: EVP framework development | Workshop with core working group, together with other stakeholders e.g. comms/marketing |  |  |  | Workshop with comms/marketing | 8000 | 29400 | 38220
| Playback and toolkit |  |  |  | Playback and toolkit (imagery not included) | 12000
| High level activation roadmap | Employer Brand Strategist | 16 | 185 |  | 2960
| High level activation roadmap | Head of Creative | 16 | 260 |  | 4160
| High level activation roadmap | Mac Operator High Spec | 12 | 110 |  | 1320
| Relationship Management | Client Manager | 4 | 130 |  | 520
| Project Management | Project Manager | 4 | 110 |  | 440
0
0
0
0
0
|  | TMP full rate-card price |  |  |  |  | 89280 | 116064
|  | Contract/framework rate-card price |  |  |  |  | 89280 | 116064
|  | Final price |  |  |  |  | 75424 | 98051.2
|  | 5% contingency to allow for conversion fluctuations |  |  |  |  | 79195.2 | 102953.76
|  | Contract/framework established discount from full TMP rate-card |  |  |  |  | 0%
|  | Further discount applied to contract/framework rates (fees only) |  |  |  |  | 15%
|  | Fee discount from TMP rate-card (fees only) |  |  |  |  | 15%
Notes:
1. All costs exclude VAT.
2. All costs are subject to detailed scope.
3. Work will not commence until sign off and all required assets are received.
4. Costs are valid for 30 days.
5. Expenses associated with the delivery of this project I.e. Travel, accommodation, subsistence, etc.) will be charged back at cost.
6. This quote excludes purchase of fonts, photography and other third-party costs.
7. All quotes are based on the information available at the time. Additional requirements will be assessed and costs/timescales may be revised accordingly.
8. There is 30 day warranty on development work. Bugs or issues that are not picked up in UAT or within 30 days of go-live are subject to additional charges.
9. Some website tasks may be completed outside of the UK.

## Optional (recommended)
TMP Cost Estimate
Project details
Client: |  | Hitachi
Project Description: |  | EVP Hypothesis
SOP Number: |  | 525634
Client contact: |  | Shannon Tracy
Date estimate produced: |  | 2025-09-10
Prepared by: |  | Ella Headlam
Version: |  | V.2
Brief / Scope
The RFP deliverables as defined by the brief Part 2 - Analysis of research - External Phase 2 - Employer branding - inspiring thinking around future stages
Price item description | Task detail | Job title | Hours | Rate £/hr | Third-party description | Line value | Item total | Item total
Phase 1 Part 2: Analysis of research - External | Index analysis of each competitor | Employer Brand Researcher | 28 | 150 |  | 4200 | 45032 | 58541.6
| Key channel analysis including careers site | Employer Brand Strategist | 32 | 185 |  | 5920
| Key channel analysis including careers site | Employer Brand Researcher | 32 | 150 |  | 4800
| Mission/Vision/Values analysis | Employer Brand Strategist | 16 | 185 |  | 2960
| Talent market insight report | Talent and Marketing Insight Consultant | 64 | 150 |  | 9600
| Playback of initial findings | Employer Brand Strategist | 8 | 185 |  | 1480
| Playback of initial findings | Mac Operator High Spec | 16 | 110 |  | 1760
External qual research
| Playback and final report ahead of messaging development | Employer Brand Strategist | 24 | 185 |  | 4440
| Playback and final report ahead of messaging development | Art Director | 16 | 130 |  | 2080
| Oversight | Head of Creative | 4 | 260 |  | 1040
| Relationship Management | Client Manager | 12 | 130 |  | 1560
| Project Management | Project Manager | 47.2 | 110 |  | 5192
Phase 2: Employer branding | Considerations for creative asset development |  |  |  | Considerations for creative asset development | 15000 | 40000 | 52000
| Testing and validation |  |  |  | Testing and validation | 15000
| Activation of new EB |  |  |  | Activation of new EB | 10000
Optional - TMPW will waive recruitment costs | Discussion guide creation for use across all 10x groups | Employer Brand Strategist | 2 | 185 |  | 370 | 14601 | 18981.3
| 10x virtual focus groups | Employer Brand Strategist | 40 | 185 |  | 7400
| Write ups and consolidation | Employer Brand Strategist | 20 | 185 |  | 3700
| Playback | Employer Brand Strategist | 1 | 185 |  | 185
| Oversight | Employer Brand Insight and Planning Director | 4 | 260 |  | 1040
| Relationship Management | Client Manager | 4 | 130 |  | 520
| Project Management | Project Manager | 12.6 | 110 |  | 1386
0
0
0
0
0
|  | TMP full rate-card price |  |  |  |  | 99633 | 129522.9
|  | Contract/framework rate-card price |  |  |  |  | 99633 | 129522.9
|  | Final price |  |  |  |  | 87706.4 | 114018.32
|  | 5% contingency to allow for conversion fluctuations |  |  |  |  | 92091.72 | 119719.236
|  | Contract/framework established discount from full TMP rate-card |  |  |  |  | 0%
|  | Further discount applied to contract/framework rates (fees only) |  |  |  |  | 15%
|  | Fee discount from TMP rate-card (fees only) |  |  |  |  | 15%
Notes:
1. All costs exclude VAT.
2. All costs are subject to detailed scope.
3. Work will not commence until sign off and all required assets are received.
4. Costs are valid for 30 days.
5. Expenses associated with the delivery of this project I.e. Travel, accommodation, subsistence, etc.) will be charged back at cost.
6. This quote excludes purchase of fonts, photography and other third-party costs.
7. All quotes are based on the information available at the time. Additional requirements will be assessed and costs/timescales may be revised accordingly.
8. There is 30 day warranty on development work. Bugs or issues that are not picked up in UAT or within 30 days of go-live are subject to additional charges.
9. Some website tasks may be completed outside of the UK.

## Overall
TMP Cost Estimate
Project details
Client: |  | Hitachi
Project Description: |  | EVP Hypothesis
SOP Number: |  | 525634
Client contact: |  | Shannon Tracy
Date estimate produced: |  | 2025-09-10
Prepared by: |  | Ella Headlam/Rachel Hogan
Version: |  | V.3
Brief / Scope
Phase 1 - The RFP deliverables as defined by the brief Part 1 - Analysis of research - Internal Part 2 - Analysis of research - External Part 3 - EVP framework development - standard costs Phase 2 - Employer branding - inspiring thinking around future stages
Price item description | Task detail | Job title | Hours | Rate £/hr | Third-party description | Line value | Item total | Item total
Phase 1 Part 1: Analysis of research - Internal | Review background docs and visionary materials - consolidate into high level actions for EVP | Employer Brand Strategist | 24 | 185 |  | 4440 | 59880 | 77844
| Map group company EVPs - provide full overview | Employer Brand Strategist | 20 | 185 |  | 3700
| Map group company EVPs - provide full overview | Employer Brand Researcher | 36 | 150 |  | 5400
| Map group company EVPs - produce high-level strawman of common links and themes | Employer Brand Strategist | 48 | 185 |  | 8880
| Map group company EVPs - Hypothesis EVP | Employer Brand Strategist | 12 | 185 |  | 2220
| Playback/Initial report | Employer Brand Strategist | 8 | 185 |  | 1480
| Playback/Initial report | Mac Operator High Spec | 16 | 110 |  | 1760
| Review of employee engagement survey - overlay against Hypothesis EVP | Employer Brand Strategist | 32 | 185 |  | 5920
| Review of employee engagement survey - overlay against Hypothesis EVP | Employer Brand Researcher | 24 | 150 |  | 3600
| Incorporate additional leader interview findings from Hitachi - revise the Hypothesis EVP | Employer Brand Strategist | 32 | 185 |  | 5920
| Incorporate additional leader interview findings from Hitachi - revise the Hypothesis EVP | Employer Brand Researcher | 24 | 150 |  | 3600
| Playback/Additional report stage | Employer Brand Strategist | 8 | 185 |  | 1480
| Playback/Additional report stage | Mac Operator High Spec | 16 | 110 |  | 1760
| Oversight | Employer Brand Insight and Planning Director | 4 | 260 |  | 1040
| Relationship Management | Client Manager | 16 | 130 |  | 2080
| Project Management | Project Manager | 60 | 110 |  | 6600
Phase 1 Part 2: Analysis of research - External | Index analysis of each competitor | Employer Brand Researcher | 28 | 150 |  | 4200 | 45032 | 58541.6
| Key channel analysis including careers site | Employer Brand Strategist | 32 | 185 |  | 5920
| Key channel analysis including careers site | Employer Brand Researcher | 32 | 150 |  | 4800
| Mission/Vision/Values analysis | Employer Brand Strategist | 16 | 185 |  | 2960
| Talent market insight report | Talent and Marketing Insight Consultant | 64 | 150 |  | 9600
| Playback of initial findings | Employer Brand Strategist | 8 | 185 |  | 1480
| Playback of initial findings | Mac Operator High Spec | 16 | 110 |  | 1760
External qual research
| Playback and final report ahead of messaging development | Employer Brand Strategist | 24 | 185 |  | 4440
| Playback and final report ahead of messaging development | Art Director | 16 | 130 |  | 2080
| Oversight | Head of Creative | 4 | 260 |  | 1040
| Relationship Management | Client Manager | 12 | 130 |  | 1560
| Project Management | Project Manager | 47.2 | 110 |  | 5192
Phase 1 Part 3: EVP framework development | Workshop with core working group, together with other stakeholders e.g. comms/marketing |  |  |  | Workshop with comms/marketing | 8000 | 29400 | 38220
| Playback and toolkit |  |  |  | Playback and toolkit (imagery not included) | 12000
| High level activation roadmap | Employer Brand Strategist | 16 | 185 |  | 2960
| High level activation roadmap | Head of Creative | 16 | 260 |  | 4160
| High level activation roadmap | Mac Operator High Spec | 12 | 110 |  | 1320
| Relationship Management | Client Manager | 4 | 130 |  | 520
| Project Management | Project Manager | 4 | 110 |  | 440
Phase 2: Employer branding | Considerations for creative asset development |  |  |  | Considerations for creative asset development | 15000 | 40000 | 52000
| Testing and validation |  |  |  | Testing and validation | 15000
| Activation of new EB |  |  |  | Activation of new EB | 10000
Optional | Discussion guide creation for use across all 10x groups | Employer Brand Strategist | 2 | 185 |  | 370 | 14601 | 18981.3
| 10x virtual focus groups | Employer Brand Strategist | 40 | 185 |  | 7400
| Write ups and consolidation | Employer Brand Strategist | 20 | 185 |  | 3700
| Playback | Employer Brand Strategist | 1 | 185 |  | 185
| Oversight | Employer Brand Insight and Planning Director | 4 | 260 |  | 1040
| Relationship Management | Client Manager | 4 | 130 |  | 520
| Project Management | Project Manager | 12.6 | 110 |  | 1386
0
0
0
0
0
|  | TMP full rate-card price |  |  |  |  | 188913 | 245586.9
|  | Contract/framework rate-card price |  |  |  |  | 188913 | 245586.9
|  | Final price |  |  |  |  | 163130.4 | 212069.52
|  | 5% contingency to allow for conversion fluctuations |  |  |  |  | 171286.92 | 222672.996
|  | Contract/framework established discount from full TMP rate-card |  |  |  |  | 0%
|  | Further discount applied to contract/framework rates (fees only) |  |  |  |  | 15%
|  | Fee discount from TMP rate-card (fees only) |  |  |  |  | 15%
Notes:
1. All costs exclude VAT.
2. All costs are subject to detailed scope.
3. Work will not commence until sign off and all required assets are received.
4. Costs are valid for 30 days.
5. Expenses associated with the delivery of this project I.e. Travel, accommodation, subsistence, etc.) will be charged back at cost.
6. This quote excludes purchase of fonts, photography and other third-party costs.
7. All quotes are based on the information available at the time. Additional requirements will be assessed and costs/timescales may be revised accordingly.
8. There is 30 day warranty on development work. Bugs or issues that are not picked up in UAT or within 30 days of go-live are subject to additional charges.
9. Some website tasks may be completed outside of the UK.